## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0021_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1375 |  |  | Transmital Date: 04/Dec/2022
Document Title:Mechanical Data Sheets For Glycol Manual Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-TR-1375 |  |  | Transmital Date: 04/Dec/2022
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D04 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد کلی: در خصوص موارد الکتریکال ضروری است،موارد ذیل در قسمت GENERAL NOTE درج گردد. |  | 1401-2294-400233 | 2023-01-10 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
.For technical requirement of electrical lv motors refer to "Data sheets for lv induction motors; DOC NO.:BK-CRS-PEDCO-120-EL-DT-0008" .Vendor shall fill in the blanks and return the compelet data sheet along with motor data sheet, Dos. No.:BK-GCS-PEDCO-120-EL-DT-0008, With his proposal .electrical motor shall be rated for the end of curve .For electrical motor description, refer to 'specification for LV induction Motors' Doc No.BK-GNRAL-PEDCO-000-EL-SP-0010. .Power Factor, efficienty, frequebt, voltage , frequent vibration and voltage variation of motor shall be specified by vendor in data sheet
2 | با توجه به بروز تغییرات در این ویرایش میبایست مدرک با وضعیت IFA انتشار یابد |  | 1401-2294-400233 | 2023-01-10 | از آنجا که پیش تر مدارک با وضعیت AFC ارسال شده و امکان برگشت به وضعیت قبل وجود ندارد، لذا مدرک مجددا با وضعیت AFC ارائه می گردد
3 | با توجه به بروز تغییرات در مدرک، ضروری است مدرک به همراه Reply sheet مشتمل بر دلایل بروز تغییرات ارسال گردد. |  | 1401-2294-400233 | 2023-01-10 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
4 | همانگونه که بار ها اعلام شده است، کلیه تغییرات مد نظر در خصوص مدارک می بایست پیش از انتشار نسخه AFC یا AFD نهایی و اعمال گردد و از انتشار شتابزده و بی پشتوانه مدارک مهندسی پرهیز شود تا نیاز به بازنگری در مراحل بعدی نباشد |  | 1401-2294-400233 | 2023-01-10 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
5 | همانگونه که در نامه شماره 01/2294/59445 بیان گردید، نسخه AFC مدارک می بایست بدون هیجگونه تغییر نسبت به ویرایش قبل که مورد تایید قرار گرفته است، تهیه و مورد استفاده قرار گیرد. |  | 1401-2294-400233 | 2023-01-10 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 11/JUL/2023