## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0021_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2107 |  |  | Transmital Date: 15/MAY/2023
Document Title: Mechanical Data Sheets For Glycol Manual Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0202-ME-TR-2107 |  |  | Transmital Date: 15/MAY/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات كارفرما بر روي ويرايش D04 (نامه شماره 400233) ، بر روي مدرك اعمال گردد سپس مدرك جايگزين شود. |  | BK-SUR-ENG-MEC-02-07642 | 2023-05-20 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature
| Date: |  |  |  |  | Date: 11/JUL/2023