## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PL-RT-0001_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1810 |  |  | Transmital Date: 1402/01/26
Document Title: Pipeline Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1810 |  |  | Transmital Date:
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مدرک ارسالی در بند اصلاح شده (صفحه 19) به نصب ادوات پایش خوردگی در ابتدا و انتهای خط لوله تاکید گردد. (در حال حاضر فقط به نصب در ابتدا تاکید شده است.) |  | 02/2294/23004 | 1402/01/26 | احتراما تعبیه ادوات پایش خوردگی در انتهای مسیر فلولاین (ورودی کلاستر) مدنظر می باشد و اصلاحات نگارشی مقتضی بر این اساس اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M.Hemmatikia | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 25/01/2023 |  |  |  |  | Date: 25/01/2023