## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1065 |  |  | Transmital Date: 11/JUN/2022
Document Title: TBE FOR GAS COMPRESSORS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-ME-TR-T-1065 |  |  | Transmital Date: 11/JUN/2022
[5 empty] | CRS No: NISOC-CRS- BK-GCS-PEDCO-120-ME-TB-0001_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه شماره BK-PEDCO-NISOC-0103-ME-LT-6059 مورخ 1401/03/21 (شماره وصول 6991)، در خصوص مدارک منضم به ترانسمیتال شماره 1065، موارد به شرح زیر به اطلاع می رساند: -ستون جداگانه ای جهت ارزش گذاری و وزن بندی هریک از مشخصات در نظر گرفته شود و بر اساس اولویت بندی تکمیل گردد. به عنوان مثال با توجه به عدم تطابق متریال و انتخاب متفاوت توسط سازندگان در این خصوص، ضروری است ستون جداگانه ای جهت ارزش گذاری و وزن بندی هریک از مشخصات در نظر گرفته شده و هزینه ارحج بر اساس اولویت تکمیل گردد. -امتیاز دهی و رتبه بندی سازندگان مطابق با بند فوق اعمال گردد. -ردیفی تحت عنوان Result در انتهای جدول اضافه گردد و نتیجه گیری نهایی پیمانکار(تایید/عدم تایید) هریک از سازندگان معرفی شده میبایست در آن درج گردد. با در نظر گرفتن موارد فوق و از آنجا که TBE ارسالی فاقد اطلاعات مکفی بوده و سازنده برتر از نظر فنی را نیز معرفی نکرده است لذا امکان بررسی و اظهار نظر در خصوص این مدرک وجود ندارد. از این رو ضروری است پیمانکار ضمن بازنگری و اصلاح موارد فوق، اقدام نمایید. |  | 01-2294-111977 | 1401/04/01 | مطابق با نامه شماره 01/2290/128283 کارفرمای اصلی محترم پروژه (ضمیمه این برگه جوابیه)، مدرک تایید گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: |  |  |  |  | Date:14/MAY/2023