## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-EL-MR-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1293 |  |  | Transmital Date: 20-Aug-2022
Document Title: PMR For Emergency Diesel Generator - W007S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-EL-TR-1293 |  |  | Transmital Date: 20-Aug-2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-EL-MR-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است که دوره آموزشی و اپراتوری دیزل ژنراتور و سیستم کنترل جهت 5 نفر در محل پروژه در مدرک لحاظ گردد. |  | 1401-2294-216140 | 1401-06-17 | در هنگام بسته شدن قرارداد با سازنده، مطابق با پیوست 12 این موضوع لحاظ خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Gh.Saadatian | Signature |  |  |  | Clarified By: | Signature
| Date: 28-Aug-22 |  |  |  |  | Date: