## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-EL-MR-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1293 |  |  | Transmital Date: 20-Aug-2022
Document Title: PMR For Emergency Diesel Generator - W007S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-EL-TR-1293 |  |  | Transmital Date: 20-Aug-2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-EL-MR-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | The next revision shall be issued after finalizing IRP vendor. |  | BK-SUR-ENG-ELE-01-05545 | 2022-08-28 | اعمال خواهد شد.
2 | Item 2: "at site condition" shall be modified to "at iso condition". |  | BK-SUR-ENG-ELE-01-05545 | 2022-08-28 | اعمال گردید.
3 | "Spare Part List and Interchangeability Record" form shall be added to this document as attachement. |  | BK-SUR-ENG-ELE-01-05545 | 2022-08-28 | فرمت مدرک MR برای همه دیسیپلینها یکسان بوده و به تأیید کافرمای محترم رسیده است. لازم به ذکر است هنگام دریافت پیشنهادفنی از سازندگان مختلف، این فرمها دریافت خواهد شد.
4 | Following documents shall be added as reference documents in section 11.1 LIST OF REFERENCE / APPLICABLE DOCUMENTS: -Specification For Painting -Document Numbering Procedure -Electrical Typical Schematic Diagrams For LV panel -LV Switchgear/MCC Single Line Diagram -Control Logic Diagram For LV Incomers and bus tie |  | BK-SUR-ENG-ELE-01-05545 | 2022-08-28 | تعدادی از این مدارک به عنوان پیوست اضافه گردید، دیگر مدارک ذکر شده مربوط به ایستگاه تقویت فشار گاز می باشد که برای تسهیلات سرچاهی معتبر نیست و مدارک مشابه آن اضافه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 28-Aug-22 |  |  |  |  | Date: