## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-LI-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0666 |  |  | Transmital Date: 2 Mar 2022
Document Title: Instrument Index For New Wells & Manifold Extension |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-IN-TR-0666 |  |  | Transmital Date: 2 Mar 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
1 | شماره مدرك BK-W007S-PEDCO-110-PR-PI-0001 (2/5) اصلاح گردد. |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | اصلاح گردید.
2 | كامنت هاي مربوط به P&ID و ديتاشيت در اين مدرك نيز در نظر گرفته شود. |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | در این مدرک لحاظ گردید.
3 | تمامي آيتم ها با دقت بيشتري پر شود مانند رديف شماره 37. |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | اصلاحات بر روی مدرک نهایی اعمال گردید.
4 | در مورد PG-1008 شفاف سازي صورت پذيرد. |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | مطابق آخرین نسخه P&ID مدرک اصلاح گردید.
5 | با توجه به ماهيت مدرك كه IFI مي باشد تمامي مسئوليت تعداد و نوع ادوات ابزاردقيق برعهده پيمانكار مي باشد. |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | آخرین نسخه مدرک AFC گردید.
6 | ادوات ابزار دقيق بر روي تانك هاي گازوئيل و آب درج گردد. |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | مطابق نوت P&ID ، این ادوات توسط سازنده تانک تهیه میشود و در لیست ابزار دقیق محسوب نشده است.
Process Comments
7 | عبارت MIX در قسمت Fluid مي بايست به HC +Water تغيير يابد. |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | اعمال گردید.
8
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Mar 2022 |  |  |  |  | Date: