## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-DW-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1628 |  |  | Transmital Date:1401/10/21
Document Title: Piping Plan - W018S |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No:PEDCO-BK-W018S-PEDCO-110-PI-DW-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اظهار نظر در خصوص مدارک فوق پس از نهایی شدن دیگر مدارک پیشنیاز ( مانند: مدل سه بعدی P&ID و ...) امکانپذیر خواهد بود. |  | 01/2294/401958 | 1401/10/21 | احتراما پاسخ موارد به پیوست ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khisravizadegan | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 17-Dec-2022 |  |  |  |  | Date: 17-Dec-2022