## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0019_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0811 |  |  | Transmital Date: 4/Des/2023
Document Title: Mechanical Data Sheets For Slug Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0202-ME-TR-T-0811 |  |  | Transmital Date: 4/Des/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0019_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| بازگشت به نامه شماره BK-HD-PEDCO-L-0653 آن پیمانکار با موضوع یاد شده به پیوست پاسخ شرکت ملی مناطق نفتخیز جنوب با نامه شماره 1402/2294/41496 مورخ 1402/02/09 مبنی بر صدور ویرایش جدید مدرک و پیشبرد گام بعدی مهندسی بلامانع بوده جهت اقدام لازم ارسال می گردد. |  | 1924/س ط ب | 1402/02/12 | با توجه به مدارک پیوست شده، مدرک با ویرایش AFC تقدیم حضورتان می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 3/JUN/2023