## QAQC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-SSGRL-PEDCO-110-ME-MR-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1733 |  |  |  | Transmital Date: | 20.Dec.2022
Document Title: PMR FOR FUEL OIL STORAGE DRUM OF WELL PADS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR- 1733 |  |  |  | Transmital Date: 20.Dec.2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-MR-0001-D00 |  |  |  | CRS Status: ‍C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion
1 | در بند 12.2، حضور نمایندگان شرکتهای PEDCO و NISOC نیز در جلسه PIM الزامی میباشد. همچنین سازنده میبایست مدارک ITP, QCP و MPS را قبل از برگزاری جلسه PIM جهت بررسی ارائه نماید. |  | BK-SUR-ENG-MEC-01-06735 | 2023-01-22 | نقطه نظر کارفرمای محترم اعمال شد.
2 | عبارت زیر در انتهای پیوست 2 اضافه گردد: "List of documents will be finalized in vendor document index and schedule" |  | BK-SUR-ENG-MEC-01-06735 | 2023-01-22 | نقطه نظر کارفرمای محترم اعمال شد.
3 | در بند 9، زمان گارانتی تجهیز 18 ماه پس از تحویل یا 12 ماه پس از راه اندازی هر کدام که زودتر اتفاق افتد در نظر گرفته شود. |  | BK-SUR-ENG-MEC-01-06735 | 2023-01-22 | نقطه نظر کارفرمای محترم اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 01/22/2023 |  |  |  |  | Date: