## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-IN-TB-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1556 |  |  | Transmital Date: 26 Oct 2022
Document Title: TBE/TBA FOR FIELD INSTRUMENTS - W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1556 |  |  | Transmital Date: 26 Oct 2022
[5 empty] | CRS No: NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شرکت ساعی سامانگر صنعت سبز برای محصول گیج دما در لیست بلند وزارت نفت تامین/تولید AVL قرار ندارد. |  | 01/2294/334204 | 1401/09/08 | این مورد به عنوان انحراف سازنده محسوب میشود. این سازنده به عنوان گزینه منتخب برای گیج دما انتخاب نخواهد شد.
2 | تعداد تجهیزات ابزار دقیق متناسب با نقشه های P&ID نهایی و به روز رسانی شود. |  | 01/2294/334204 | 1401/09/08 | مدرک مطابق آخرین نسخه P&ID به روز رسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 9 Nov 2022 |  |  |  |  | Date: