## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0007_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1333 |  |  | Transmital Date: 28 Aug 2022
Document Title: Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1333 |  |  | Transmital Date: 28 Aug 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05639 | 2022-09-12 | ملاحظه گردید.
2 | Line No با آخرين PID ارائه شده تناقض دارد. موارد مجددا بررسي و ارائه گردد. |  | BK-SUR-ENG-INS-01-05639 | 2022-09-12 | تصحیح گردید.
3 | نسخه مدارك مرجع درج گردد. |  | BK-SUR-ENG-INS-01-05639 | 2022-09-12 | پیرو جلسات برگزار شده نسخه مدارک P&ID درج گردید.
4 | اطلاعات PURCHASING DATA به will be finalized later تغيير پيدا كند. |  | BK-SUR-ENG-INS-01-05639 | 2022-09-12 | اعمال گردید.
5 | در خصوص Over Range Protection به صراحت در مدرك بيان شود. ارائه مدرك به اين صورت قابل قبول نمي باشد. |  | BK-SUR-ENG-INS-01-05639 | 2022-09-12 | اعمال گردید.
6 | هر دو مورد Instrument Range و Calibration range در جدول پيوست مشخص شود. |  | BK-SUR-ENG-INS-01-05639 | 2022-09-12 | اعمال گردید.
7 | جهت چك كردن نهايي اطلاعات مربوط به ترانسميتر و المان جريان با هم ارائه گردد. |  | BK-SUR-ENG-INS-01-05639 | 2022-09-12 | در بخش TRANSMITTER و به طور خاص در ردیف های 20،19و21 ارائه گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 12 Sep 2022 |  |  |  |  | Date: