## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0009_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0914 |  |  | Transmital Date: 08 May 2022
Document Title: Data Sheets For Corrosion Coupon/ Probe - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR- 1333 |  |  | Transmital Date: 08 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدرك پيش نياز مانند specification for instrumentation تاييد نشده است و به ويژه به اينكه قسمت مربوط به CC و CP داراي كامنت اساسي مي باشد. در صورت هر گونه تغيير در موارد در اين مدرك نيز منعكس شود. |  | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | مدرک مطابق آخرین نسخه از مدارک پیش نیاز ارائه گردید. لازم به ذکر است که موارد ذکر شده در مدرک SPECIFICATION FOR INSTRUMENTATION تماما در مدرک دیتاشیت ارائه گردیده است.
2 | آيتم 43، VTA به VTC تغيير پيدا كند. |  | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | آیتم 43 VTC گردید موارد دیگر بخش COUPON مدرک با صلاح دید وندور تعیین خواهد گردید.
3 | اطلاعات مربوط به Purchase از VTA به will be finalized Later تغيير پيدا كند. |  | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | اعمال گردید.
4 | تغييرات با Revision Mark مشخص شود. |  | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | اعمال گردید.
5 | اطلاعات فرآيندي بر اساس آخرين PFD و P&ID بروز رساني گردد. |  | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 24 May 2022 |  |  |  |  | Date: