## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-EL-DT-0002-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1934 |  |  | Transmital Date: 06-Mar-2023
Document Title: Data Sheets for UPS - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0112-EL-TR-1934 |  |  | Transmital Date: 06-Mar-2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-EL-DT-0002-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | This document shall be revised after finalizing or minor comments on following documents: -Calculation Note for UPS System - Extension of Binak B/C Manifold -UPS Single Line Diagram - Extension of Binak B/C Manifold -Electrical Power & Control Cable List - Extension of Binak B/C Manifold |  | BK-SUR-ENG-ELE-01-05735 | 2022-09-21 | آخرین ویرایش مدرک ابزاردقیق که با ترنسمیتال شماره 1899 برای آن کارفرمای محترم ارسال شده است، مورد بهره برداری قرار گرفته و محاسبات و برگه داده به روزرسانی شد. |  |  | See below item 2.
2 | See above item 1: تاييد نهايي اين مدرك منوط به نهايي سازي مدرك I&C Power Consumption Summary - Extension of Binak B/C Manifold (BK-W007S-PEDCO-110-IN-LI-0007) بخش ابزاردقيق ميباشد. |  | BK-SUR-ENG-ELE-01-07206 | 2023-03-13 | لیست بار ابزاردقیق در نظر گرفته شده برای انجام محاسبات، ترنسمیتال 1899 این بخش است که ملاک سایزینگ بخش برق می باشد. در صورت هر گونه تغییر در مدارک ابزاردقیق این مدرک ویرایش خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 14-Mar-23 |  |  |  |  | Date: