## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0010_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1319 |  |  | Transmital Date:22-Aug-2022
Architectural Drawing For CCTV Rack Room- Binak PU |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-T-1319 |  |  | Transmital Date: 22-Aug-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0010_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند1 |  | 1401-2294-240288 | 1401/07/06 | موقعیت مکانی طبق شرح کار در کی پلان مدرک موجود است . در مورد کدF.G.L.در بازنگری بعدی مقدار دقیق این مورد بعد از برداشت نقشه برداری مربوطه درج خواهدشد.
2 | بند2 |  | 1401-2294-240288 | 1401/07/06 | اعمال گردید
3 | بند3 |  | 1401-2294-240288 | 1401/07/06 | اعمال گردید
4 | بند4 |  | 1401-2294-240288 | 1401/07/06 | اعمال گردید
5 | بند5 |  | 1401-2294-240288 | 1401/07/06 | دیتیل های مربوطه اضافه گردید
6 | بند6 |  | 1401-2294-240288 | 1401/07/06 | اعمال گردید
7 | بند7 |  | 1401-2294-240288 | 1401/07/06 | اعمال گردید
8 | بند8 |  | 1401-2294-240288 | 1401/07/06 | اعمال گردید
9 | بند9 |  | 1401-2294-240288 | 1401/07/06 | باتوجه به توافقات صورت گرفته فی مابین نمای آجری در نظرگرفته شده است
10 | بند10 |  | 1401-2294-240288 | 1401/07/06 | هردو نقشه سقف کاذب و جدول نازک کاری اضافه گردید
11 | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
12
13 | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
14 | Commented By: | Signature |  |  |  | Clarified By: | Signature
15
16 | Date: |  |  |  |  | Date:
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
Legend
Signature