## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-RT-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1710 |  |  | Transmital Date:-18-Dec-2022
Document Title: Piping Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1710 |  |  | Transmital Date:18-Dec-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو تاکیدات قبلی، جنس خط خروجی مایعات مخازن Knock Out Drum، Closed Drain, Suction Drum، Discharge Drum برای قبل و بعد از شیر کنترلی با لحاظ نمودن خورندگی سیال مشخص گردد. به علاوه ویرایش جدید مدرک MFD بر اساس اصلاحات انجام شده این مدرک همراه با ویرایش بعدی ارسال گردد. |  | 1402-2294-86482 | 1402/03/06 | نقطه نظر کارفرمای محترم اعمال گردید. این موارد درویرایش بعدی MFD هم اعمال می گردد. لازم به ذکر است که در P&ID متریال خطوط کاملا مشخص شده داست.
2 | بر اساس ویرایش جدید مدرک PFD و P&ID برخی ازتجهیزات از جمله Degassing Drum و Storage Tank حذف شده اند. لذا مدرک مطالعات خوردگی براساس ویرایش جدید مدارک فرآیندی اصلاح و موارد غیر مرتبط حذف/اصلاح گردد. |  | 1402-2294-86482 | 1402/03/06 | نقطه نظر کارفرمای محترم اعمال گردید.
3 | خط خروجی Slug Catcher از جنس SS316L در نظر گرفته شده است. باتوجه به اینکه مایعات خروجی Slug Ctacher از این خط عبور می کند، موضوع عدم وجود کلر با توجه به محدودیت های جنس انتخاب شده (SS316L) بررسی گردد. همچنین برای لوله کشی بعد از شیر کنترلی حد مجاز خوردگی 3 میلی متر لحاظ شده که باتوجه به خورندگی سیال و جنس انتخاب شده برای ظرف و سامانه لوله کشی بالادست حداقل حد مجاز خوردگی 6 میلیمتر لحاظ گردد. |  | 1402-2294-86482 | 1402/03/06 | * موضوع عدم وجود کلر قبلا توسط بخش فرآیند تایید گردیده است. به Note1 جدول محاسبه خوردگی پایپینک مراجعه شود. *نقطه نظر کارفرمای محترم اعمال گردید و در ویرایش بعدی MFD اصلاح می گردد .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Hemmatikia | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 07/06/2022 |  |  |  |  | Date: 07/06/2022