## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-RT-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1710 |  |  | Transmital Date: 18-DEC-2022
Document Title: Piping Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1710 |  |  | Transmital Date: 18-DEC-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | نقطه نظر کارفرما محترم اعمال گردید. |  |  | Closed
2 | با توجه به اينكه در مدرك SPECIFICATION FOR LINING براي تجهيز V-2107 پوشش داخلي ذكر شده است در حاليكه در مدرك Corrosion Study & Material Selection Report اشاره اي به آن نگرديده است، لذا اصلاحات لازم بايستي بطور مطابق انجام شود. در صورت نياز بايستي اين مورد در مدرك Corrosion Study & Material Selection Report اضافه گردد. |  | BK-SUR-ENG-PIP-01-06481 | 2022-12-21 | برای تجهیز Closed DRAIN (V-2107) پوشش داخلی در نظر گرفته شده است. شماره تجهیز بروز رسانی شد.
3 | در جدول بخش 11 مدرك SPECIFICATION FOR LINING و همچنين مدرك Corrosion Study & Material Selection Report براي مخزن Elevated Potable Water Tank سيستم رنگ داخلي تعريف شده و جنس مخزن نيز CS ذكر گرديده است ولي در ديتاشيت مكانيكال مخزن مذكور جنس آن HDPE ذكر شده است. موضوع بررسي و اصلاحات لازم در مدارك انجام شود. |  | BK-SUR-ENG-PIP-01-06481 | 2022-12-21 | مطابق آخرین دیتا شیت تجهیز آب آتش آشامیدنی از جنس کربن استیل با پوشش می باشد. دیتاشیت به همراه ریپلای شیت ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M.Hemmatikia | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 21-Dec-2022 |  |  |  |  | Date: 21-Dec-2022