## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ST-DW-0010-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1853 |  |  | Transmital Date:2/8/2023
Document Title: Standard Drawing for Lighting pole foundation Plan & Details |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-ST-T-1853 |  |  | Transmital Date: 2/8/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-473018 | 1401/12/10 | تغییر عنوان انجام گردید
2 |  |  | 1401-2294-473018 | 1401/12/10 | لیست مدارک اصلاح گردید
3 |  |  | 1401-2294-473018 | 1401/12/10 | همانطور که در نامه شماره 393696-2294-1400 آن کارفرمای محترم بیان شده است، استفاده از برج روشنایی 15 متری Lattice مطابق با نقشه استاندارد شرکت نفت ملاک عمل قرار گرفته است که همگی در نقشه های سیویل منعکس شده است. همچنین در مدرک “MTO For Lighting & Small Powers (BK-GCS-PEDCO-120-EL-MT-0002)” تمامی مشخصات فنی مورد نیاز پایه های روشنایی لحاظ خواهد شد. لذا خواهشمند است از ارائه مشخصات فنی پایه های روشنایی در این مدرک صرف نظر گردد.
4 |  |  | 1401-2294-473018 | 1401/12/10 | TEMPLATE مورد نظر توسط تولید کننده تهیه می گردد
5 |  |  | 1401-2294-473018 | 1401/12/10 | دیتایل مذکور حذف گردید
6 |  |  | 1401-2294-473018 | 1401/12/10 | pos میلگردهای سنجاقی مشخص گردید
7 |  |  | 1401-2294-473018 | 1401/12/10 | درشیت شماره 23 مدرک TYPICAL INSTALATION DETAILS & NOTES FOR LIGHTING SYSTEM دیتایل مربوط یه اسلیو ها مشخص و با توجه به جزئیات اشاره شده ، اسلیو خارج از بتن پدستال قرار می گیرد
8 |  |  | 1401-2294-473018 | 1401/12/10 | طول همپوشانی اضافه گردید
|  |  | 1401-2294-473018 | 1401/12/10 | آرماتور فوق اصلاح گردید
9 |  |  | 1401-2294-473018 | 1401/12/10 | موارد با R.Mark مشخص گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: