## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-MR-0010_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1124 |  |  | Transmital Date: 27-Jun-2022
Document Title: PMR For Local Control Station (LCS) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-EL-TR-1124 |  |  | Transmital Date: 27-Jun-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-EL-MR-0010_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | PEDCO EL: A seperat section as title "Scope of Work" shall be added and shall be explained in detail such as Engineering, Design, Procurement of all material, Packing, Shipping and Transportation, As built documents and drawings, Training, etc. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | با توجه به اینکه فرمت MR بین تمامی دیسیپلینها به یک صورت می باشد، لذا از تغییر در فرمت مورد تأیید کارفرما صرف نظر شده است.
2 | PEDCO EL, General: Reference document and title of the project shall be added to table. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اعمال گردید.
3 | PEDCO EL: "Spare Part List and Interchangeability Record" form shall be added to this document as attachement. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | فرمت مدرک MR برای همه دیسیپلینها یکسان بوده و به تأیید کافرمای محترم رسیده است. لازم به ذکر است هنگام دریافت پیشنهادفنی از سازندگان مختلف، این فرمها دریافت خواهد شد.
4 | Following documents shall be added as reference documents in section 11.1 LIST OF REFERENCE / APPLICABLE DOCUMENTS:: -Specification For Painting -Packing, Marking, Transportation Procedure -Document Numbering Procedure |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اعمال گردید.
5 | PEDCO EL: 11.2 VENDOR DOCUMENTS MIN. REQUIREMENT: It seems some mentioned documents in list is not related to scope of work and supply. It shall be rechecked and modified. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اصلاح گردید.
6 | PEDCO EL: 5.2 EXCLUSIONS: Some items has been missed base on sentences. It shall be rechecked and modified. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اصلاح گردید.
7 | در بند 5.1.1، عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اعمال گردید.
8 | در بند 6: 1-عبارت "Project ITP Procedure" به "دستورالعمل بازرسي خريد و ساخت كالا" تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اعمال گردید.
9 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل FDB Requirements اضافه گردد. 2-دستورالعمل Packing, Marking, Transportation Procedure اضافه گردد. 3-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اعمال گردید.
10 | در جدول Attachments 2 (Vendor Documents Minimum Requirements): 1. در رديف 1، عبارت "See Attachmen 2" حذف گردد. 2. عبارت "List of Documents will be Finalized in Vendor Document Index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-ELE-01-05049 | 2022-07-11 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 11-Jul-22 |  |  |  |  | Date: