## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0004_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1246 |  |  | Transmital Date: 3/AGU/2022
Document Title: PMR For Gas Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-T-1246 |  |  | Transmital Date: 3/AGU/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0004_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه شماره 00/2294/162504 بیان گردیدمدارک MR مدارک مهندسی تفصیلی مربوطه (مانند مشخصات فنی، داده برگ ها، PMS، MTOو ...) می بایست تولید گردد، چرا که تمامی مدارک مذکور در مورد هر پکیج خرید، می بایست با درج عنوان آن در متن، ضمیمه PMR ها شوند. از آنجایی که مدارک مهندسی مرتبط تا کنون نهایی نشده اند، |  | 01/2294/216173 | 1401/06/17 | با توجه به جزیی بودن نقطه نظرات بر مدارک پیوست MR و بروز رسانی شدن مدارک، لذا از کارفرمای محترم خواهشمند است جهت پیشبرد امور مهندسی خرید، مدرک در دستور کار بررسی قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: |  |  |  |  | Date: