## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0013_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1178 |  |  | Transmital Date: 23 Jul 2022
Document Title: Data Sheets For Orifice Plate/Restriction Orifice |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1178 |  |  | Transmital Date: 23 Jul 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comment
1 | سر برگ صفحه 8 اصلاح گردد. |  | 01/2294/233417 | 2022-08-21 | مطابق نظر کارفرمای محترم ، اصلاح شد.
2 | مدرک زیر به عنوان مرجع در نظر گرفته شود. INSTRUMENT AND CONTROL SYSTEM DESIGN CRITERIA |  | 01/2294/233417 | 2022-08-21 | مطابق نظر کارفرمای محترم ، اعمال شد.
3 | لازم است ضریب β مطابق با استاندارد اطلاح و Sizing مجددا انجام گردد. |  | 01/2294/233417 | 2022-08-21 | با توجه به مذاکرات شفاهی با کارفرمای اصلی پروژه (NISOC) مقرر گردید در شرایط کنونی پروژه و به منظور عدم جلوگیری از تغییر سایز خطوط لوله، ضریب β توسط سازنده تجهیز فوق نهایی گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: