## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0006_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2050 |  |  | Transmital Date: 30/APR/2023
Document Title: Specification For Air Compressor Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0202-ME-TR-2050 |  |  | Transmital Date: 30/APR/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D05 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم ارسال ويرايش قبلي اين مدرك با ترانسميتال 0690 به ذينفع اصلي ، لازم است نسبت به تغيير ويرايش اين مدرك به D05 و جايگزيني مدرك پس از اعمال نظرات ، اقدام شود.متعاقبا نسبت به حذف مدرك از ترانسميتال 0690 اقدام نماييد. |  | BK-SUR-ENG-MEC-02-07546 | 2023-05-03 | .نقطه نظر کارفرمای محترم مد نظر قرار گرفته شد
Instrument comments:
1 | Specification for Instrument and Control of Package Unit System در ليست مدارك مرجع اضافه گردد. |  | BK-SUR-ENG-MEC-02-07546 | 2023-05-03 | .نقطه نظر کارفرمای محترم مد نظر قرار گرفته شد
2 | بازگشت به نقطه نظر كارفرما بر روي مدرك MR طي نامه 30940، در خصوص سيستم كنترل موارد در اين مدرك نيز لحاظ و بروز رساني گردد. |  | BK-SUR-ENG-MEC-02-07546 | 2023-05-03 | .نقطه نظر کارفرمای محترم مد نظر قرار گرفته شد
3 | در بخش 5-4، Controls and Instrumentation فقط به سيستم كنترل اشاره كرده است. در خصوص ادوات ابزاردقيق، كنترل مانند Due point Analyzer و نيازمندي هاي آن در اين مدرك اشاره گردد يا به مدارك مرتبط با آن اشاره شود. |  | BK-SUR-ENG-MEC-02-07546 | 2023-05-03 | .نقطه نظر کارفرمای محترم مد نظر قرار گرفته شد
Electrical comments:
1 | ويرايش استاندارد IPS-M-EL-143 از 2 به 3 اصلاح گردد. |  | BK-SUR-ENG-MEC-02-07546 | 2023-05-03 | مطابق نظر کارفرمای محترم اصلاح شده است.
2 | ويرايش IPS-M-E-144 از 2 به 4 اصلاح گردد. |  | BK-SUR-ENG-MEC-02-07546 | 2023-05-03 | مطابق نظر کارفرمای محترم اصلاح شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature
| Date: |  |  |  |  | Date:8/8/2023