## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-AR-DW-0004_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1917 |  |  | Transmital Date: 01/MAR/2023
Document Title: Architectural Drawing For Security Building of Well Pads - W007S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-T-1917 |  |  | Transmital Date:01/MAR/2023
[5 empty] | CRS No:NISOC-CRS-BK-W007S-PEDCO-110-AR-DW-0004-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند 1 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
2 | بند 2 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
3 | بند 3 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
4 | بند 4 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
5 | بند 5 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
6 | بند 6 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
7 | بند 7 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
8 | بند 8 |  | 1401-2294-5332 | 1402/01/08 | در این مدرک محور C موجود نمی باشد، لطفا محل دقیق وال پست پیشنهادی شفاف سازی گردد.
9 | بند 9 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
10 | بند 10 |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: