## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-CN-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1749 |  |  | Transmital Date: 01-Jan-2023
Document Title: Calculation Note For Lighting System of Well Pads Switchgear Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-1749 |  |  | Transmital Date: 01-Jan-2023
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جهت پخش نور بهتر و یکنواخت در سطح اتاق پیرو بند 5 نامه شماره 280865 مورخ 1401/08/03 پیشنهاد می شود، چراغ ها در سقف اتاق نصب و تعداد آنها به دو عدد افزایش یابد. |  | 1401-2294-419775 | 1401-11-03 | چراغ اتاق باتری به سقف آویزان و اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Gh.Saadatian | Signature |  |  |  | Clarified By: | Signature
| Date: 16-Jan-23 |  |  |  |  | Date: