## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0035_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1373 |  |  | Transmital Date: 07/Sep/2022
Document Title: Mechanical Data Sheets For Glycol Drain Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1373 |  |  | Transmital Date: 07/Sep/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please be informed that some of the comments have considered as "NOTED" but it has not been implemented in the datasheet, so it has been requested to confirm that "these comments shall be followed by the Hirgan in technical clarification"; so there is no need to issue the documents again. |  | BK-SUR-ENG-MEC-01-05827 | 2022-09-03 | Noted, these comments such as hydrotest pressure and minimum flow will be finalized at vendor's offer stage and technical clarification.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 13/JUN/2023