## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1703 |  |  | Transmital Date: 18 May 2022
Document Title: Control Room Layout & Arrangement Drawing |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1703 |  |  | Transmital Date: 18 May 2022
[5 empty] | CRS No: NIOEC-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نامه 92236 مورخ 1401/03/17 این امور با موضوع جمع بندی نظرات در خصوص معماری اتاق کنترل اعلان می گردد. پس از انجام تغییرات جمع بندی شده. این مدرک مجددا برای بررسی ارسال گردد |  | 1401-2294-388761 | 1401/10/13 | با توجه به آخرین توافقات صورت گرفته از ساختمان کنترل موجود با در نظر گرفتن اتاق های اضافه شده جهت نصب پنل های کنترلی و work station استفاده شده است
2 | تجهیزات اتاق مهندسی مشخص گردند. |  | 1401-2294-388761 | 1401/10/13 | نظر کارفرمای محترم اعمال گردد
3 | مسیر ترنچ های ورودی به اتاق کنترل نشان داده شود |  | 1401-2294-388761 | 1401/10/13 | نظر کارفرمای محترم اعمال گردد
4 | تعداد و نوع WORK STATION ها با توجه به آخرین نظرات این امور بر مدرک CONTROL SYSTEM BLOCK DIAGRAM CONFIGURATION بروز رسانی گردد. |  | 1401-2294-388761 | 1401/10/13 | تعداد و نوع work station ها با توجه به آخرین توافقات صورت گرفته در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 1 Jun 2022 |  |  |  |  | Date: