## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1211 |  |  | Transmital Date: 27-Jul-2022
Document Title: Instrument Earthing Typical Diagram |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1211 |  |  | Transmital Date: 27-Jul-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص موارد Reply sheet نظر خاصی مطرح نمی باشد |  | 1401-2294-233554 | 1401/06/31 | -
2 | در محدوده ایستگاه گازی بینک سیستم ارتینگ جدید می باشد. اتصال به ارتینگ موجود پذیرفته نیست. عبارت ( Existing - by other ) در مدرک اصلاح گردد. |  | 1401-2294-233554 | 1401/06/31 | نظرات کارفرمای محترم در مدرک اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 15 Aug 2022 |  |  |  |  | Date: