## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-EL-MR-0016_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1965 |  |  | Transmital Date: 25-Mar-2023
Document Title: PMR For DC Charger- W007S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-1965 |  |  | Transmital Date: 25-Mar-2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-EL-MR-0016_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
EL. Comments.
1 | In case of any changes in prerequisite documents, this document shall be revised. |  | BK-SUR-ENG-ELE-02-07272 | 2023-03-28 | در صورت نیاز و تغییر سایزینگ، مدرک به روزرسانی خواهد شد.
2 | documents listed in attachment 2, are not related to DC Charger. Vendor document min. requirements tables shall be totally revised. |  | BK-SUR-ENG-ELE-02-07272 | 2023-03-28 | اعمال گردید. لازم به ذرک است این مدارک همگی در VPIS به روزرسانی خواهد شد و مدارک مربتط در حیطه کاری وندور قرار میگیرد.
QC. Comments.
1 | در بند 6: -عبارت "QC Plan" و "Quality Control Plan" به "Inspection and Test Plan (ITP)" تغيير يابد. |  | BK-SUR-ENG-ELE-02-07272 | 2023-03-28 | اعمال گردید.
2 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-ELE-02-07272 | 2023-03-28 | در زمان عقد قرارداد این مدارک از وندور دریافت خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 26-Mar-23 |  |  |  |  | Date: