## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-MT-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1483 |  |  | Transmital Date:11-Oct-2022
Document Title: MTO For Fittings |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1483 |  |  | Transmital Date:11-Oct-2022
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-PI-MT-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نهايي شدن مدارك پيش نياز مانند PMS و Wall Thickness Calculation Report و مدل سه بعدي و نقشه هاي ايزومتريك مربوط به ايستگاه تقويت فشار GCS قبل از ارسال اين مدرك ضروري مي باشد.لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد نهايي اين مدرك به لحاظ جنس متريال و مشخصات فني پس از نهايي شدن مدارك ذكر شده مقدور مي باشد. بديهي است مسئوليت كامل تطابق متريال و مشخصات فني با PMS مورد تأييد پروژه و مسئوليت درستي تعداد اقلام و هرگونه كسري متريال بر عهده آن پيمانكار مي باشد. |  | BK-SUR-ENG-PIP-01-05905 | 2022-10-16 | مدارک مذکور ارسال شده اند. نقطه نظر کارفرمای محترم مد نظر قرار می گیرد.
2 | بقيه كامنتها بصورت مارك شده در مدرك به پيوست ارسال مي گردد |  | BK-SUR-ENG-PIP-01-05905 | 2022-10-16 | پاسخ در همان فایل ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 16.Oct.2022 |  |  |  |  | Date: 16.Oct.2022