## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-ME-MR-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1808 |  |  | Transmital Date: 18/Jan/2023
Document Title: PMR For Pig Traps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1808 |  |  | Transmital Date: 18/Jan/2023
[5 empty] | CRS No:NISOC-CRS-BK-PPL-PEDCO-320-ME-MR-0001-D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده و لیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبط مهندسی و درج نسخ تایید شده (AFC) است. معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق، نهایی سازی مدارک پیش نیاز(که در پیوست 1 مدرک اشاره شده است) در دستور کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 1401/2294/466406 | 1401/12/07 | با توجه به تایید بیشتر مدارک پیوست 1 و عدم وجود نقطه نظر کلیدی بر مدارک ضمیمه MR ، لذا از کارفرمای محترم خواهشمند است جهت تسریع در امور خرید، بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
Date: