## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-MR-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1594 |  |  | Transmital Date: 21.Nov.2022
Document Title: PMR FOR GASKETS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1594 |  |  | Transmital Date: 21.Nov.2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-MR-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده و لیکن ارسال نسخه بعدی مدارک فوق منوط به تهایی سازی مدارک مرتبطه مهندسی و درج نسخه تایید شده (AFC) است و معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق، نهایی سازی مدارک پیش نیاز ( که در پیوست 1 مدارک اشاره شده است) در دستور کار تیم مهندسی آن پیمانکار فرار گیرد. در ضمن MTO کالا نیز جزو مدارک خرید میبایست درج گردد. مزید تاکید اعلام می گردد از آنجا که مسئولیت طراحی تقصیلی پروژه جزو تعهدات پیمانکار پروژه است و همچنین با استناد به وضعیت مدارک ارسالی (IFI) مسئولیت کامل عدم تطابق متریال مندرج در این مدرک صدرالذکر (مشخصات فنی یا تعداد) در مرحله سفارش گذاری و خرید بر عهده پیمانکار است و لذا پیگیری فرآیند خرید با پذیرش تبعات پیش گفته از سوی پیمانکار بلامانع است. در ضمن نهایی سازی مدارک پیش نیاز نیز در اولویت کار تیم مهندسی ان پیمانکار قرار گیرد. |  | 1401-2294-367199 | 1401/09/29 | نفطه نظر کارفرمای محترم مد نظر قرار می گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M. Torkaman | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature | M.Fakharian
| Date: 29/11/2022 |  |  |  |  | Date: 29/11/2022