## QAQC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-BK14-PEDCO-110-PI-MR-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1544 |  |  |  | Transmital Date: | 2022-10-25
Document Title: PMR For Pipes - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1544 |  |  |  | Transmital Date: 25-Oct-2022
[5 empty] | CRS No: PEDCO-CRS-BK-BK14-PEDCO-110-PI-MR-0001_D00 |  |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نهايي شدن مدارك پيش نياز مانند PMS و Piping Wall Thickness Calculation و MTO و آيزومتريكهاي مربوط به سر چاه قبل از ارسال اين مدرك ضروري مي باشد. لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد نهايي اين مدرك به لحاظ جنس متريال و مشخصات فني و تعداد اقلام پس از نهايي شدن مدارك ذكر شده مقدور مي باشد. |  | BK-SUR-ENG-PIP-01-06158 | 2022-11-12 | مدارک مذکور ارسال و تایید شده است.
2 | در مدرك فقط لوله هاي 4" مربوط به Burn Pit در نظر گرفته شده است. با توجه به عنوان مدرك و شرح كار براي چاههاي تعميري بايستي تمامي لوله ها از جمله لوله هاي سرچاهي كه براي تعميرات و تغيير جانمايي لوله ها بعلت نصب پمپ IRP مورد نياز مي باشند لحاظ گردد. |  | BK-SUR-ENG-PIP-01-06158 | 2022-11-12 | اصلاحات لازم اعمال گردید.
3 | در بخش 5.1.1 جمله اول به Row 3 of listed pipes in MTO for Pipes اشاره شده است در حاليكه در MTO فقط رديف ROW 1 درج شده است . اصلاحات لازم اعمال گردد. |  | BK-SUR-ENG-PIP-01-06158 | 2022-11-12 | اصلاحات لازم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 8-Nov-2022 |  |  |  |  | Date: 8-Nov-2022