## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MR-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1594 |  |  | Transmital Date: 21.Nov.2022
Document Title: PMR FOR FITTINGS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1594 |  |  | Transmital Date: 21.Nov.2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-MR-0002_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 5.1.3 موارد زير اضافه گردد : 1. ذكر گردد كه گواهينامه متريال بر اساس BS EN 10204 / ISO 10474, Type 3.2 certificate (or certificates) باشد. 2. All Materials specified with NACE shall meet the requirements of Sour Services. Sour services’ materials shall meet the requirement of NACE MR0175/ISO 15156 standard. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید.
2 | در بند 6: 1-عبارت Data Sheets به Project Specifications تغيير يابد. 2. سطح بازرسي براي Flanges and Fittings به Level 2 تغيير يابد. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید.
3 | در جدول Attachment 1(List of Reference/Applicable Documents): 1- دستورالعمل Packing, Marking, Transportation Procedure اضافه شود. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید.
4 | عبارت " List of Documents Will be Finalized in Vendor Document index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید.
5 | نهايي شدن مدارك پيش نياز مانند PMS و Piping Wall Thickness Calculation و MTO For Fittings مربوط به GCS قبل از ارسال اين مدرك ضروري مي باشد. لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد نهايي اين مدرك پس از نهايي شدن مدارك مذكور مقدور مي باشد. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | این مدارک ارسال شده اند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M. Torkaman | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature | M.Fakharian
| Date: 29/11/2022 |  |  |  |  | Date: 29/11/2022