## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-LD-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1110 |  |  | Transmital Date: 22-Jun-2022
Document Title: Control System /ESD Logic Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1110 |  |  | Transmital Date: 22-Jun-2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-LD-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عنوان مدرك در خصوص سيگنالهاي Pig Launcher area شفاف سازي صورت پذيرد. |  | BK-SUR-ENG-INS-01-05018 | 2022-07-06 | با توجه به نظر کارفرمای محترم اعمال گردید
2 | Title صفحات اصلاح گردد. |  | BK-SUR-ENG-INS-01-05018 | 2022-07-06 | اصلاح شد.
3 | با توجه به مذاكرات انجام شده در جلسه HAZOP در مورد shutdown در زمان Total shutdown واحد سياهمكان اصلاحات انجام گيرد. |  | BK-SUR-ENG-INS-01-05018 | 2022-07-06 | اصلاح شد.
4 | با توجه به مذاكرات انجام شده در جلسه HAZOP در مورد نحوه عملكرد open و Close واحد سياهمكان اصلاحات انجام گيرد. |  | BK-SUR-ENG-INS-01-05018 | 2022-07-06 | با توجه به نظر کارفرمای محترم اعمال گردید
5 | مدارك مربوط به سيستم كنترل و ESD بصورت مشترك ارائه شده است (I/O ليست) ، اين درحاليست كه در رويژن هاي پيشين مربوط به MDL، مدارك بصورت مجزا ارائه شده است و ارائه مدارك بصورت مشترك روال تاييد شده اي نمي باشد. |  | BK-SUR-ENG-INS-01-05018 | 2022-07-06 | مدرک مطابق آخرین MDL ارسال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 6 Jul 2022 |  |  |  |  | Date: