## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-PY-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1178 |  |  | Transmital Date: 23 Jul 2022
Document Title: Instrument Location Layout |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1178 |  |  | Transmital Date: 23 Jul 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-PY-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | ملاحظه گردید
2 | با توجه به نقشه P&ID، شماتيك مورد نظر براي ناحيه GCS نيز در اين مدرك نمايش داده شود. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | با توجه به اینکه توضیحات لازم در NOTE 1 آورده شده است برای جلوگیری از تکرار اطلاعات خواهشمند است به بسته GCS مراجعه شود.لازم به ذکر است کلیه ابزاردقیق محوطه LUNCHER در بسته GCS خریداری می شود.
3 | شماتيك با استفاده از نتايج به دست آمده از جلسات HAZID/HAZOP/SIL مجددا بررسي و اصلاح گردد. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | نقشه با توجه به آخرین مدل و توافقات بروزرسانی گردید
4 | ليست مدارك مرجع اضافه گردد. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | اعمال گردید
5 | legend تكميل گردد. مواردي مانند CC و ZI اضافه گردد. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | اعمال گردید
6 | Elevation تجهيزات به كار رفته نشان داده شود. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | اعمال گردید
7 | ادوات با P&ID مغايرت دارد. مواردي مانند TDS اضافه گردد. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | نقشه با توجه به آخرین مدل و توافقات بروزرسانی گردید
8 | بر اساس كامنت هاي پيشين TG بر روي خط پيگراني قرار دارد. اصلاح گردد. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | اصلاح گردید
9 | كامنت هاي بخش Piping به پيوست آمده است. |  | BK-SUR-ENG-INS-01-05365 | 2022-08-06 | پیوست گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 6 Aug 2022 |  |  |  |  | Date: