## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1488 |  |  | Transmital Date: 12 Oct 2022
Document Title: Instrument Hook-up Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1488 |  |  | Transmital Date: 12 Oct 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مورد 3 از Reply sheet بین Pressure Gauge و منیفولد Union نیاز می باشد و بصورت VTC لحاظ گردد |  | 1401-2294-305024 | 1401/08/19 | بصورت note در مدرک اضافه گردید
2 | بقیه موارد نظر خاصی مطرح نمی باشد |  | 1401-2294-305024 | 1401/08/19 | ملاحظه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 25 Oct 2022 |  |  |  |  | Date: