## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1488 |  |  | Transmital Date: 12 Oct 2022
Document Title: Instrument Hook-up Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1488 |  |  | Transmital Date: 12 Oct 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05974 | 2022-10-25 | ملاحظه گردید.
2 | مسئوليت تطابق تعداد ادوات ارائه شده در MTO و مدرك بر عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05974 | 2022-10-25 | ملاحظه گردید.
3 | در خصوص مدرك Instrument Hook-up Diagram-D02 با توجه به اينكه هنوز مدرك Piping Assembly Drawing كه دراين مدرك ارجاع داده شده دريافت نگرديده است لذا نظر نهايي پس از ارائه مدرك مربوطه اعلام مي گردد. |  | BK-SUR-ENG-INS-01-05974 | 2022-10-25 | مدرک Piping Assembly Drawing ارسال شده است
4 | Flow Direction مشخص شود. |  | BK-SUR-ENG-INS-01-05974 | 2022-10-25 | انجام شد
5 | Hook-Up مربوط به Float Type با جزئيات كامل نشان داده شود و صفحه مدرك ارجاع شده بطور مشخص بيان گردد |  | BK-SUR-ENG-INS-01-05974 | 2022-10-25 | انجام شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 25 Oct 2022 |  |  |  |  | Date: