## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0007_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1568 |  |  | Transmital Date: 13/DeC/2021
Document Title: Mechanical Data Sheets For Diesel Oil Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-ME-TR-1568 |  |  | Transmital Date: 13/DeC/2021
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-ME-DT-0007_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ابعاد مخزن با آخرین ویرایش مدرک P&ID همخوان نمی باشد. ضروری است یکسان سازی گردد. |  | 01/2294/480503 | 1401/12/15 | ابعاد مخزن مطابق با آخرین رویژن پروسس دیتاشیت و مدرک P&ID اصلاح شد.
2 | حداقل ضخامت پوسته مطابق با استاندارد IPS-G-ME-150 در نظر گرفته شود. |  | 01/2294/480503 | 1401/12/15 | به دلیل تحت فشار نبودن این مخزن، استاندارد مذکور در دیتاشیت به عنوان مرجع درنظر گرفته نشده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: 01/03/2021 |  |  |  |  | Date: 6/21/2023