## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-PEDCO-320-PI-SP-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1202 |  |  | Transmital Date: 26-Jul-2022
Document Title: Piping Material Specification |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1202 |  |  | Transmital Date:26-Jul-2022
[5 empty] | CRS No: CRS-BK-PPL-PEDCO-320-PI-SP-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نهايي نشدن مدرك مطالعات خوردگي در صورت تغيير در ميزان حد مجاز خورگي مدرك بايستي به روز رساني گردد. |  | BK-SUR-ENG-PIP-01-05280 | 2022-07-30 | احتراما مدارک پیش نیاز ارسال شده است. ضمنا این مدرک پیرو توافقات انجام شده طی نامه شماره س ط ب / 4034 ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:30-Jul-2022 |  |  |  |  | Date:30-Jul-2022