## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-MT-0003-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1696 |  |  | Transmital Date:14-Dec-2022
Document Title: MTO For Flangess-Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1669 |  |  | Transmital Date:14-Dec-2022
[5 empty] | CRS No:NISOC-CRS-BK-W007S-PEDCO-110-PI-MT-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک MTOمی بایست پس از تدوین و نهایی شدن کلیه مدارک مهندسی تقصیلی مربوطه (مانند مشخصات فنی، ئداده برگ ها، Corrosion Study، Wall Thickness PMS و 3D MOdel Review) تولید گردد. لذا از آنجاییکه تاکنون مدارک پیش گفته نهایی نشده اند، صحه گذاری و تایید این مدرک به لحاظ جنس متریال و مشخصات فنی اقلام در شرایط کنونی از سوی این امور میسز نیست. مزید تاکید اعلام می گردد از آنجا که مسئولیت طراحی تقصیلی پروژه جزو تعهدات پیمانکار پروژه است و همچنین با استناد به وضعیت مدارک ارسالی (IFI) مسئولیت کامل عدم تطابق متریال مندرج در این مدرک صدرالذکر (مشخصات فنی یا تعداد) در مرحله سفارش گذاری و خرید بر عهده پیمانکار است و لذا پیگیری فرآیند خرید با پذیرش تبعات پیش گفته از سوی پیمانکار بلامانع است. در ضمن نهایی سازی مدارک پیش نیاز نیز در اولویت کار تیم مهندسی ان پیمانکار قرار گیرد. |  | 01/2294/400172 | 1401/10/20 | نفطه نظر کارفرمای مجترم مد نظر قرار می گیر و مدارک ذکر شده نهایی شده اند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 26.Dec.2022 |  |  |  |  | Date: 26.Dec.2022