## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-MT-0003-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1696 |  |  | Transmital Date:14-Dec-2022
Document Title: MTO For Flangess-Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1669 |  |  | Transmital Date:14-Dec-2022
[5 empty] | CRS No:PEDCO-CRS-BK-W007S-PEDCO-110-PI-MT-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نهايي شدن مدارك پيش نياز مانند PMS و Wall Thickness Calculation Report و مدل سه بعدي و نقشه هاي ايزومتريك مربوط به منيفولد قبل از ارسال اين مدرك ضروري مي باشد. لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد آن به لحاظ جنس متريال و مشخصات فني پس از نهايي شدن مدارك ذكر شده مقدور مي باشد. بديهي است مسئوليت كامل تطابق متريال و مشخصات فني با PMS مورد تأييد پروژه و مسئوليت درستي تعداد اقلام و هرگونه كسري متريال بر عهده آن پيمانكار مي باشد. |  | BK-SUR-ENG-PIP-01-06534 | 2022-12-26 | این مدارک ارسال شده اند.
2 | با توجه به اينكه MTO از خروجي PDMS تهيه مي شود لذا در MTO ستوني اضافه شود و كلاس مخصوص به هر آيتم در مقابلش نوشته شود. |  | BK-SUR-ENG-PIP-01-06534 | 2022-12-26 | باتوجه به اینکه خروجی PDMS تجمیع می گردد و یک آیتم ممکن است به چند کلاس متعلق باشد امکان درج کلاس وجود نداشته و ضرورتی هم ندارد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 26.Dec.2022 |  |  |  |  | Date: 26.Dec.2022