## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK15-PEDCO-110-GT-RT-0001_D00 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1146 |  |  | Transmital Date:7/6/2022
Document Title: Geotechnical Investigation Report - BK15 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-1146 |  |  | Transmital Date:7/6/2022
[5 empty] | CRS No:NISOC-CRS-BK-BK15-PEDCO-110-GT-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-144182 | 1401/04/27 | اصلاح گردید
2 |  |  | 1401-2294-144182 | 1401/04/27 | ------
3 |  |  | 1401-2294-144182 | 1401/04/27 | ------
4 |  |  | 1401-2294-144182 | 1401/04/27 | مسئولیت گزارش بر عهده مشاور ژئوتکنیک می باشد. در محدوده و منطقه مورد مطالعه خاک بصورت همگن و مطابق مبحث 7 بین 50تا 200کتر(مسیرخط لوله) قابل تعمیم است. گزارش دریافتی از مشاور ژئوتکمیک بر اساس و مطابق با شرح کار ژئوتکنیکی صورت پذیرفته که قبلا طی ترنسمیتال رسمی برای آن کارفرمای محترم ارسال گردیده است. لازم بذکر است جانمایی کریدور خط لوله و محل لوکیشن ها مطابق بر اسناد پیمان انجام شده است
5 |  |  | 1401-2294-144182 | 1401/04/27 | در پیوست ارائه شده است
6 |  |  | 1401-2294-144182 | 1401/04/27 | لایه های مشاهده شده در محل سنگی بوده و امکان انجام آزمایشات آزمایشگاهی جهت تعیین نفوذپذیری وجود ندارد ، لذا با توجه به نفوذپذیری لایه های سنگی ، مقدار ارائه شده در گزارش مطابق مراجع قابل پیشنها است
7 |  |  | 1401-2294-144182 | 1401/04/27 | در متن گزارش و پیوست ارائه شده است
8 |  |  | 1401-2294-144182 | 1401/04/27 | به نشریه مذکور اشاره شده است
9 |  |  | 1401-2294-144182 | 1401/04/27 | در محل گمانه های حفاری به پدیده کارست برخورد نشده است
10 |  |  | 1401-2294-144182 | 1401/04/27 | موارد در قسمت توصیه فنی لحاظ شده است
11 |  |  | 1401-2294-144182 | 1401/04/27 | در قسمت توصیه کلی و منابع قرضه و اساس و زیر اساس ارائه گردیده است
12 |  |  | 1401-2294-144182 | 1401/04/27 | در بند 4-7 و 5-7 اشاره شده است
13 |  |  | 1401-2294-144182 | 1401/04/27 | نتایج آزمایش شیمیایی در پیوست ارائه شده است
14 |  |  | 1401-2294-144182 | 1401/04/27 | موارد در قسمت منابع قرضه ارایه شده است
15 |  |  | 1401-2294-144182 | 1401/04/27 | اضافه گردید
16 |  |  | 1401-2294-144182 | 1401/04/27 | بنا بر نظر کارفرما بخش GIS حذف گردید
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: