## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1059 |  |  | Transmital Date:6/11/2022
Document Title: Geotechnical Investigation Report - W008N |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GTT-1059 |  |  | Transmital Date:6/11/2022
[5 empty] | CRS No:NISOC-CRS-BK-W008N-PEDCO-110-GT-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-111566 | 1401/03/31 | پارامترها و جزئیات در پیوست ارائه گردیده است
2 |  |  | 1401-2294-111566 | 1401/03/31 | مطالعات هیدرولوژی به پیوست ارسال می گردد
3 |  |  | 1401-2294-111566 | 1401/03/31 | باتوجه به جنس لایه ها و مراجع موجود و همچنین تجربیات قبلی مشاور ، نفوذ پذیر لایه ها کم و لازم بذکر است به دلیل سفتی لایه های مذکور امکان اخذ نمونه دست نخورده مناسب برای انجام آزمایش نفوذ پذیری در لایه های خاکی وجود نداشته است
4 |  |  | 1401-2294-111566 | 1401/03/31 | گزارش بررسی منابع قرضه در پیوست 8 و پارامترهای اساس و زیر اساس در بخش 2-8 توصیه فنی لحاظ گردیده است
5 |  |  | 1401-2294-111566 | 1401/03/31 | در منابع قرضه اشاره شده است و سازه خاصی موجود نمی باشد
6 |  |  | 1401-2294-111566 | 1401/03/31 | در محل های مورد نیاز ارائه شده است
7 |  |  | 1401-2294-111566 | 1401/03/31 | در محل گمانه های حفاری شده به پدیده کارست برخورد نشده است
8 |  |  | 1401-2294-111566 | 1401/03/31 | نمودارها و لاگ گمانه ها در پیوست موجود می باشد
|  |  | 1401-2294-111566 | 1401/03/31 | در قسمت توصیه کلی و منابع قرضه و اساس و زیر اساس راهکار ها ارائه شده است
|  |  | 1401-2294-111566 | 1401/03/31 | موارد به گزارش اضافه گردید
10 |  |  | 1401-2294-111566 | 1401/03/31 | گزارش شامل مراجع می باشد
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: