## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W035-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1059 |  |  | Transmital Date:6/11/2022
Document Title: Geotechnical Investigation Report - W035 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-1059 |  |  | Transmital Date:6/11/2022
[5 empty] | CRS No:NISOC-CRS-BK-W035-PEDCO-110-GT-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-111566 | 1401/03/31 | اطلاعات ذکر شده در پیوست ارائه شده است
2 |  |  | 1401-2294-111566 | 1401/03/31 | با توجه به جنس لایه ها و مراجع موجود و همچنین تجربیات قبلی مشاور ، نفوذ پذیری لایه ها کم برآورد گردیده و لازم بذکر است به دلیل سفتی لایه ها امکان اخذ نمونه دست نخورده مناسب برای انجام آزمایش نفوذپذیری در لایه های خاکی وجود نداشته است
3 |  |  | 1401-2294-111566 | 1401/03/31 | در متن گزارش و پیوست ارائه شده است
4 |  |  | 1401-2294-111566 | 1401/03/31 | در منابع قرضه اشاره شده است
5 |  |  | 1401-2294-111566 | 1401/03/31 | در محل برخورد شالوده با آب در صورت نیاز انجام شده است
6 |  |  | 1401-2294-111566 | 1401/03/31 | سازه خاصی موجود نمی باشد
7 |  |  | 1401-2294-111566 | 1401/03/31 | در صورت برخورد ارائه شده است
8 |  |  | 1401-2294-111566 | 1401/03/31 | در محل های مورد نیاز ارائه شده است
9 |  |  | 1401-2294-111566 | 1401/03/31 | در محل گمانه های حفاری شده به پدیده کارست برخورد نشده است
10 |  |  | 1401-2294-111566 | 1401/03/31 | لاگ های مربوطه در پیوست ارائه شده است
11 |  |  | 1401-2294-111566 | 1401/03/31 | در توصیه کلی و منابع قرضه و اساس و زیر اساس اشاره شده است
12 |  |  | 1401-2294-111566 | 1401/03/31 | در بند 4-7 و 5-7 ارائه شده است
13 |  |  | 1401-2294-111566 | 1401/03/31 | اضافه گردید
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: