## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1567 |  |  | Transmital Date:10/30/2022
Document Title: Geotechnical Investigation Report - W046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-1567 |  |  | Transmital Date:10/30/2022
[5 empty] | CRS No:NISOC-CRS-BK-W046S-PEDCO-110-GT-RT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-324278 | 1401/09/01 | طول خطوط لوله جریان و مسیر برق رسانی به گزارش ژئوتکنیک اضافه شده است
2 |  |  | 1401-2294-324278 | 1401/09/01 | در محل گمانه های حفاری شده به پدیده کارست برخورد نشده است
3 |  |  | 1401-2294-324278 | 1401/09/01 | گزارش بررسی منابع قرضه در پیوست 8 و پارامترهای اساس و زیر اساس در بخش 2-8 توصیه فنی لحاظ گردیده است
4 |  |  | 1401-2294-324278 | 1401/09/01 | در فصل پنجم به مشکلات لایه بندی خاک اشاره و در توصیه های کلی راهکاربرخورد با مشکلات ارائه شده است
5 |  |  | 1401-2294-324278 | 1401/09/01 | با توجه به همگن بودن خاک مشاهده شده در منطقه و محدوده ، نمودارهای ارائه شده برای کلیه ساختمانها و سازه ها قابل بهره برداری می باشد
6 |  |  | 1401-2294-324278 | 1401/09/01 | در بند 4-7 (شیب مجاز لایه های خاک) برای اعماق مختلف ارائه شده است
7 |  |  | 1401-2294-324278 | 1401/09/01 | پیوست مذکور حذف گردید
8 |  |  | 1401-2294-324278 | 1401/09/01 | مورد تایید می باشد
9 |  |  | 1401-2294-324278 | 1401/09/01 | در حین عملیات اجرایی تکمیل گمانه ها ، حفاری مورد نیاز انجام و از خدمات کارشناسان ژئوتکنیک ذی صلاح استفاده خواهد شد
10 |  |  | 1401-2294-324278 | 1401/09/01 | در ردیف 6-3 گزارش هیدرولوژی ، عمق یخبندان لحاظ گردیده است
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: