## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-DW-0001_D03 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2077 |  |  | Transmital Date: 5/9/2023
Document Title: Civil and Structural drawings - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-2077 |  |  | Transmital Date: 5/9/2023
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-CV-DW-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-99988 | 1402/03/16 | طراحی، مطابق با آخرین هماهنگی ها و نظرات کارفرما انجام شده است. متعاقبا مستندات مربوطه ارائه می گردد.
2 |  |  | 1402-2294-99988 | 1402/03/16 | در نقشه Civil Layout مسیر خط جدید و طول آن نشان داده شده است. مشخصات مربوطه درج گردید.
3 |  |  | 1402-2294-99988 | 1402/03/16 | در محدوده گودال سوخت عرض 22 متری جهت تامین گردش ماشین آلات درنظر گرفته شده است.
4 |  |  | 1402-2294-99988 | 1402/03/16 | اصلاح شد. لازم به ذکر است فایل تقدیم شد ه از چندین فایل مختلف تولید می گردد و جهت بررسی شیت های Layout1 و Access Road ملاک قرار گیرد.
5 |  |  | 1402-2294-99988 | 1402/03/16 | دیتایل در محل 20 متری سمت کورال اضافه گردید
6 |  |  | 1402-2294-99988 | 1402/03/16 | اصلاحات کلی در نظرگرفته شده است
7 |  |  | 1402-2294-99988 | 1402/03/16 | پوزهای 12 و 13 در نظر گرفته شده است
8 |  |  | 1402-2294-99988 | 1402/03/16 | در مقاطع 10 و 11 میلگردهای حرارتی در نظر گرفته شده است
9 |  |  | 1402-2294-99988 | 1402/03/16 | تعداد میلگرد پوز 1 اصلاح گردید
10 |  |  | 1402-2294-99988 | 1402/03/16 | همانطور که مستحضرید گودال سوخت این چاه موجود است. بر این اساس در نقشه های ارائه شده ساختار هندسی موجود آن به کمک عملیات خاکی، ترمیم و احیا شده است. در صورت اصلاح شیب خاکریز حجم داخلی گودال کاهش می یابد.
11 |  |  | 1402-2294-99988 | 1402/03/16 | گودالهای آب و گل به صورت بتنی دیده شده است(جزئیات آن در نقشه ها درج گردیده است). بند 8 شرح کار ناظر به سناریویی است که گودالهای آب و گل موجود در پایین دست چاه ترمیم گردد حال آنکه بر اساس طرح پسماند جدید، چیدمان و ابعاد گودالها بر اساس نیازهای حفاری تغییر یافته است.
12 |  |  | 1402-2294-99988 | 1402/03/16 | اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: