## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK05-PEDCO-110-PI-PY-0001_D00 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1817 |  |  | Transmital Date:1/23/2023
Document Title: Plot Plan Drawing – BK05 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR- 1817 |  |  | Transmital Date: 1/23/2023
[5 empty] | CRS No: NISOC-CRS-BK-BK05-PEDCO-110-PI-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختمان برق به میزان 1.5 متر به سمت جنوب جابجا گردد. |  | 1402/2291/11928 | 1402/01/16 | احتراما با توجه به وضعیت فنس موقعیت کلی ساختمان تغییر کرده است.
1 | فاصله بین دیزل جنراتور و مخزن گازئیل 6 متر باشد. |  | 1402/2291/11928 | 1402/01/16 | احتراما نقطه نظر اعمال گردید.
1 | نحوه قرارگیری دیزل جنراتور هم راستا با فنس شمالی باشد. |  | 1402/2291/11928 | 1402/01/16 | احتراما نقطه نظر اعمال گردید.
1 | یک درب نفر رو با توجه به جهت باد غالب و توپوگرافب در نظر گرفته شود. |  | 1402/2291/11928 | 1402/01/16 | احتراما نقطه نظر پس از نهایی شدن مدرک CIVIL LAYOUT چاه در نظر گرفته می شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khisravizadegan | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 29-Jan-2023 |  |  |  |  | Date: 29-Jan-2023