## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK12-PEDCO-110-PI-PY-0001_D00 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1824 |  |  | Transmital Date: 1/24/2023
Document Title: Plot Plan Drawing – BK12 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1824 |  |  | Transmital Date: 1/24/2023
[5 empty] | CRS No: NISOC-CRS-BK-BK12-PEDCO-110-PI-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختمان برق در فاصبه 6 متری از درب ضلع شمالی قرار داده شود و شلتر دیزل ژنراتور و تانک سوخت در راستای فنس شمالی کنار آن قرار داده شود (فضای آزاد حداقل 83 متر) |  | 1402/2291/11928 | 1402/01/16 | احتراما نقطه نظر اعمال گردید.
1 | بررسی گردد در صورت امکان جهت ایجاد تردد بهتر ساختمان نگهبانی جابجا گردد. |  | 1402/2291/11928 | 1402/01/16 | احتراما با توجه به توپوگرافی محل چاه تنها موقعیت درب اصلاح گردید (از داخل محوطه پد بتنی خارج گردید).
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khisravizadegan | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 30-Jan-2023 |  |  |  |  | Date: 30-Jan-2023