## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PI-PY-0002_D01 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2059 |  |  | Transmital Date:5/1/2023
Document Title: Plot Plan Drawing - W007S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2059 |  |  | Transmital Date: 5/1/2023
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-PI-PY-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص بند یک صورتجلسه مورخ 19/11/1401 اتاقک نگهبانی به صورت صحیح به داخل به درون سایت منتقل نشده است که می بایست اصلاح گردد. همچنین در خصوص چیدمان درب نفر رو در ویرایش بعدی مدل اظهار نظر خواهد شد. |  | 1402/2294/73113 | 1402/02/30 | احتراما نقطه نظر اعمال گردد.
2 | با توجه به نظر نماینده اداره مهندسی فرآورش و گسترش ستاد مبنی بر تجربیات موجود در زمینه تلمبه های IRP نصب شده، مقرر گردید به منظور سهولت در راهبری و نظارت بر عملکرد پمپ یونیت سرچاهی، استراکچر پمپ به میزان 18درجه چرخش ایجاد شود و پس از آن خط تولیدی و کودال سوزا با زانو به سمت فنس برگردانده و از آن خارج گردد. |  | 1402/2294/73113 | 1402/02/30 | احتراما نقطه نظر اعمال گردد.
3 | با توجه به عوارض منطقه درب خروج دوم مورد تایید نماینده ایمنی ستاد قرار گرفت. |  | 1402/2294/73113 | 1402/02/30 | احتراما کامنت مد نظر قرار می گردد.
3 | فنس محوطه گنتری نشان داده نشده است. |  | 1402/2294/73113 | 1402/02/30 | احتراما نقطه نظر مربوط به مدل سه بعدی می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: