## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-PI-DW-0001_D01 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2059 |  |  | Transmital Date:01 May 2023
Document Title: Plot Plan Drawing - W008N |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2059 |  |  | Transmital Date: 01 May 2023
[5 empty] | CRS No: NISOC-CRS-BK-W008N-PEDCO-110-PI-DW-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اعلام نظر همکاران شرکت گچساران درب بزرگ تردد خودرو روبروی مرکز محوطه چاه جابجا گردد. |  | 1402/2294/73113 | 1402/02/30 | احتراما نقطه نظر اعمال گردید
2 | در محوطه گودال سوخت فنس در نظر گرفته شود. |  | 1402/2294/73113 | 1402/02/30 | احتراما نقطه نظر اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khosravizadegan | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 6-May-2023 |  |  |  |  | Date: 6-May-2023